## Sheet1
Sprint | Date | Scrum Master | To-Do Task | Assigned To | Story Points | In-Progress | Completed
Sprint 1 | Jan 28 – Feb 1 | Vraj Patel | Set up project repository and version control | Vraj Patel | 2 | Landing Page/Home Page
Sprint 1 | Jan 28 – Feb 1 | Vraj Patel | Set up backend framework | Divy Patel | 3
Sprint 1 | Jan 28 – Feb 1 | Vraj Patel | Configure initial database schema | Divy Patel | 3
Sprint 1 | Jan 28 – Feb 1 | Vraj Patel | Establish code standards and security baseline | Jay Panchal | 2
Sprint 1 | Jan 28 – Feb 1 | Vraj Patel | Create initial UI prototype/wireframes | Jinil Patel | 3
Sprint 1 | Jan 28 – Feb 1 | Vraj Patel | Gather requirements and draft product backlog | Ayush Prabhakar | 2
Sprint 1 | Jan 28 – Feb 1 | Vraj Patel | Integrate front-end and back-end dev environments | Vraj Patel | 2
Sprint 2 | Feb 4 – Feb 8 | Divy Patel | Develop user registration UI | Jinil Patel | 3 | Set up project repository and version control | Set up backend framework
Sprint 2 | Feb 4 – Feb 8 | Divy Patel | Implement OTP generation and email service | Jay Panchal | 5 | Configure initial database schema | Establish code standards and security baseline
Sprint 2 | Feb 4 – Feb 8 | Divy Patel | Create OTP verification API endpoint | Divy Patel | 3 |  | Create initial UI prototype/wireframes
Sprint 2 | Feb 4 – Feb 8 | Divy Patel | Build frontend OTP entry screen | Jinil Patel | 2 |  | Gather requirements and draft product backlog
Sprint 2 | Feb 4 – Feb 8 | Divy Patel | Integrate frontend with auth APIs | Vraj Patel | 3 |  | Integrate front-end and back-end dev environments
Sprint 2 | Feb 4 – Feb 8 | Divy Patel | Implement session management with JWT | Divy Patel | 2 |  | Landing Page/Home Page
Sprint 2 | Feb 4 – Feb 8 | Divy Patel | Testing: Verify signup flow end-to-end | Ayush Prabhakar | 2
Sprint 3 | Feb 11 – Feb 15 | Jinil Patel | Define user roles in system | Divy Patel | 3 | Implement OTP generation and email service | Develop user registration UI
Sprint 3 | Feb 11 – Feb 15 | Jinil Patel | Implement role-based authorization on backend | Jay Panchal | 3 | Integrate frontend with auth APIs | Create OTP verification API endpoint
Sprint 3 | Feb 11 – Feb 15 | Jinil Patel | Implement role-based routing on frontend | Vraj Patel | 2 |  | Build frontend OTP entry screen
Sprint 3 | Feb 11 – Feb 15 | Jinil Patel | Build basic dashboard UI skeleton | Jinil Patel | 5 |  | Implement session management with JWT
Sprint 3 | Feb 11 – Feb 15 | Jinil Patel | Create landing page | Jinil Patel | 3 |  | Testing: Verify signup flow end-to-end
Sprint 3 | Feb 11 – Feb 15 | Jinil Patel | Testing: Ensure access control | Ayush Prabhakar | 2
Sprint 4 | Feb 18 – Feb 22 | Jay Panchal | Design 'Create New Event' form UI | Vraj Patel | 3 | Everything is Completed from last sprint | Define user roles in system
Sprint 4 | Feb 18 – Feb 22 | Jay Panchal | Implement live preview of event details | Vraj Patel | 3 |  | Implement role-based authorization on backend
Sprint 4 | Feb 18 – Feb 22 | Jay Panchal | Set up Event data model in database | Divy Patel | 2 |  | Implement role-based routing on frontend
Sprint 4 | Feb 18 – Feb 22 | Jay Panchal | Develop backend API to create event request | Jay Panchal | 3 |  | Build basic dashboard UI skeleton
Sprint 4 | Feb 18 – Feb 22 | Jay Panchal | Connect frontend form to backend | Jinil Patel | 2 |  | Create landing page
Sprint 4 | Feb 18 – Feb 22 | Jay Panchal | Testing: Create sample event requests | Ayush Prabhakar | 2 |  | Testing: Ensure access control
Sprint 5 | Feb 25 – Mar 1 | Ayush Prabhakar | Build 'Approve Events' admin page UI | Vraj Patel | 3 | Implement live preview of event details | Design 'Create New Event' form UI
Sprint 5 | Feb 25 – Mar 1 | Ayush Prabhakar | Implement backend API to fetch pending events | Divy Patel | 2 | Connect frontend form to backend | Testing: Create sample event requests
Sprint 5 | Feb 25 – Mar 1 | Ayush Prabhakar | Implement backend API to approve an event | Divy Patel | 3 | Set up Event data model in database | Develop backend API to create event request
Sprint 5 | Feb 25 – Mar 1 | Ayush Prabhakar | Implement option to reject event requests | Jay Panchal | 3
Sprint 5 | Feb 25 – Mar 1 | Ayush Prabhakar | Integrate approval/rejection actions on frontend | Jinil Patel | 2
Sprint 5 | Feb 25 – Mar 1 | Ayush Prabhakar | Send notification email upon approval/rejection | Jay Panchal | 2
Sprint 5 | Feb 25 – Mar 1 | Ayush Prabhakar | Testing: Verify admin approval process | Ayush Prabhakar | 2
Sprint 6 | Mar 4 – Mar 8 | Divy Patel | Create database of venues/classrooms | Vraj Patel | 2 | Implement backend API to approve an event | Build 'Approve Events' admin page UI
Sprint 6 | Mar 4 – Mar 8 | Divy Patel | Backend API to check room availability | Divy Patel | 5 | Implement option to reject event requests | Implement backend API to fetch pending events
Sprint 6 | Mar 4 – Mar 8 | Divy Patel | Backend API to book a classroom | Jay Panchal | 5 |  | Implement option to reject event requests
Sprint 6 | Mar 4 – Mar 8 | Divy Patel | Build 'Book Classroom' UI page | Jinil Patel | 5 |  | Send notification email upon approval/rejection
Sprint 6 | Mar 4 – Mar 8 | Divy Patel | Integrate booking flow with events | Vraj Patel | 3 |  | Testing: Verify admin approval process
Sprint 6 | Mar 4 – Mar 8 | Divy Patel | Testing: Ensure double-booking prevention | Ayush Prabhakar | 3
Sprint 7 | Mar 11 – Mar 15 | Jinil Patel | Extend 'Create Event' form to include service requests | Vraj Patel | 3 | Build 'Book Classroom' UI page | Create database of venues/classrooms
Sprint 7 | Mar 11 – Mar 15 | Jinil Patel | Update event data model to store requested services | Divy Patel | 3 |  | Backend API to check room availability
Sprint 7 | Mar 11 – Mar 15 | Jinil Patel | Create 'Service Request' sub-model | Divy Patel | 3 |  | Backend API to book a classroom
Sprint 7 | Mar 11 – Mar 15 | Jinil Patel | Generate service request entries upon approval | Jay Panchal | 5 |  | Integrate booking flow with events
Sprint 7 | Mar 11 – Mar 15 | Jinil Patel | Build Department Dashboard UI | Jinil Patel | 3 |  | Testing: Ensure double-booking prevention
Sprint 7 | Mar 11 – Mar 15 | Jinil Patel | Backend API to fetch service requests | Divy Patel | 3
Sprint 7 | Mar 11 – Mar 15 | Jinil Patel | Backend API to update request status | Jay Panchal | 3
Sprint 7 | Mar 11 – Mar 15 | Jinil Patel | Integrate department UI with backend | Vraj Patel | 2
Sprint 7 | Mar 11 – Mar 15 | Jinil Patel | Testing: Validate service request flow | Ayush Prabhakar | 3
Sprint 8 | Mar 18 – Mar 22 | Jay Panchal | Develop 'Manage Events' page UI | Jinil Patel | 3 | Backend API to fetch service requests | Extend 'Create Event' form to include service requests
Sprint 8 | Mar 18 – Mar 22 | Jay Panchal | Backend API to retrieve events by owner | Divy Patel | 2 | Backend API to update request status | Update event data model to store requested services
Sprint 8 | Mar 18 – Mar 22 | Jay Panchal | Event edit functionality on frontend | Vraj Patel | 3 |  | Create 'Service Request' sub-model
Sprint 8 | Mar 18 – Mar 22 | Jay Panchal | Backend API to update event details | Divy Patel | 3 |  | Generate service request entries upon approval
Sprint 8 | Mar 18 – Mar 22 | Jay Panchal | Implement event cancellation option | Vraj Patel | 2 |  | Build Department Dashboard UI
Sprint 8 | Mar 18 – Mar 22 | Jay Panchal | Backend API to cancel an event | Jay Panchal | 3 |  | Integrate department UI with backend
Sprint 8 | Mar 18 – Mar 22 | Jay Panchal | Integrate edit and cancel actions | Jinil Patel | 2 |  | Testing: Validate service request flow
Sprint 8 | Mar 18 – Mar 22 | Jay Panchal | Testing: Verify event edits and cancellations | Ayush Prabhakar | 2
Sprint 9 | Mar 25 – Mar 29 | Vraj Patel | Build 'Upcoming Events' page UI | Jinil Patel | 3 | Event edit functionality on frontend | Develop 'Manage Events' page UI
Sprint 9 | Mar 25 – Mar 29 | Vraj Patel | Backend API to list upcoming events | Divy Patel | 2 | Implement event cancellation option | Backend API to retrieve events by owner
Sprint 9 | Mar 25 – Mar 29 | Vraj Patel | Implement RSVP functionality on backend | Divy Patel | 3 |  | Backend API to update event details
Sprint 9 | Mar 25 – Mar 29 | Vraj Patel | Implement ability to cancel RSVP | Jay Panchal | 2 |  | Backend API to cancel an event
Sprint 9 | Mar 25 – Mar 29 | Vraj Patel | Frontend RSVP actions integration | Vraj Patel | 3 |  | Integrate edit and cancel actions
Sprint 9 | Mar 25 – Mar 29 | Vraj Patel | Update event model to track RSVPs | Jay Panchal | 2 |  | Testing: Verify event edits and cancellations
Sprint 9 | Mar 25 – Mar 29 | Vraj Patel | Testing: RSVP flow validation | Ayush Prabhakar | 2
Sprint 10 | Apr 1 – Apr 5 | Ayush Prabhakar | Define key metrics to display | Ayush Prabhakar | 2 | Implement RSVP functionality on backend | Build 'Upcoming Events' page UI
Sprint 10 | Apr 1 – Apr 5 | Ayush Prabhakar | Backend aggregation for analytics | Divy Patel | 3 |  | Backend API to list upcoming events
Sprint 10 | Apr 1 – Apr 5 | Ayush Prabhakar | Integrate chating library | Vraj Patel | 3 |  | Implement ability to cancel RSVP
Sprint 10 | Apr 1 – Apr 5 | Ayush Prabhakar | Build Chat Dashboard UI | Jinil Patel | 5 |  | Frontend RSVP actions integration
Sprint 10 | Apr 1 – Apr 5 | Ayush Prabhakar | Display real-time data | Vraj Patel | 2 |  | Update event model to track RSVPs
Sprint 10 | Apr 1 – Apr 5 | Ayush Prabhakar | Testing: Verify Chat real-time accuracy | Ayush Prabhakar | 2 |  | Testing: RSVP flow validation
Sprint 11 | Apr 8 – Apr 12 | Jinil Patel | Make UI responsive on mobile | Vraj Patel | 5 | Everything is Completed from last sprint | Define key metrics to display
Sprint 11 | Apr 8 – Apr 12 | Jinil Patel | UI/UX review and improvements | Jinil Patel | 2 |  | Backend aggregation for analytics
Sprint 11 | Apr 8 – Apr 12 | Jinil Patel | Implement event reminder emails | Jay Panchal | 3 |  | Integrate chating library
Sprint 11 | Apr 8 – Apr 12 | Jinil Patel | Deploy landing page content | Jinil Patel | 2 |  | Build Chat Dashboard UI
Sprint 11 | Apr 8 – Apr 12 | Jinil Patel | Cross-browser and mobile testing | Ayush Prabhakar | 2 |  | Display real-time data
Sprint 11 | Apr 8 – Apr 12 | Jinil Patel | User feedback implementation | Divy Patel | 2 |  | Testing: Verify Chat real-time accuracy
Sprint 12 | Apr 15 – Apr 19 | Divy Patel | End-to-end testing | Ayush Prabhakar | 5 | Everything is Completed from last sprint | Make UI responsive on mobile
Sprint 12 | Apr 15 – Apr 19 | Divy Patel | Security audit and penetration testing | Jay Panchal | 3 |  | UI/UX review and improvements
Sprint 12 | Apr 15 – Apr 19 | Divy Patel | Bug fixes and security patching | Jinil Patel | 3 |  | Implement event reminder emails
Sprint 12 | Apr 15 – Apr 19 | Divy Patel | Optimize database and performance | Divy Patel | 2 |  | Deploy landing page content
Sprint 12 | Apr 15 – Apr 19 | Divy Patel | Documentation and user guides | Ayush Prabhakar | 3 |  | Cross-browser and mobile testing
Sprint 12 | Apr 15 – Apr 19 | Divy Patel | Deploy backend to production | Divy Patel | 2 |  | User feedback implementation
Sprint 12 | Apr 15 – Apr 19 | Divy Patel | Final front-end deployment test | Vraj Patel | 1
Sprint 13 | Apr 22 – Apr 26 | Vraj Patel | Final bug-fix on vercel | Vraj Patel | 3 | Everything is Completed from last sprint | End-to-end testing
Sprint 13 | Apr 22 – Apr 26 | Vraj Patel | Code refactoring and cleanup | Jinil Patel | 2 |  | Security audit and penetration testing
Sprint 13 | Apr 22 – Apr 26 | Vraj Patel | Final documentation updates | Ayush Prabhakar | 3 |  | Bug fixes and security patching
Sprint 13 | Apr 22 – Apr 26 | Vraj Patel | Project presentation | Jay Panchal | 2 |  | Optimize database and performance
Sprint 13 | Apr 22 – Apr 26 | Vraj Patel | Final deployment and release tagging | Divy Patel | 1 |  | Documentation and user guides
Deploy backend to production
Final front-end deployment test
Sprint 14 | Apr 27 - Apr 29 | Ayush Prabhakar | Review Everything |  |  | Everything is Completed from last sprint | Final bug-fix on vercel
Code refactoring and cleanup
Final documentation updates
Project presentation
Final deployment and release tagging