## Sheet1
Sprint | Total_Tasks | Total_Story_Points | Tasks_To_Be_Done
Sprint 1 | 7 | 17 | Set up project repository and version control; Set up backend framework; Configure initial database schema; Establish code standards and security baseline; Create initial UI prototype/wireframes; Gather requirements and draft product backlog; Integrate front-end and back-end dev environments
Sprint 10 | 6 | 17 | Define key metrics to display; Backend aggregation for analytics; Integrate chating library; Build Chat Dashboard UI; Display real-time data; Testing: Verify Chat real-time accuracy
Sprint 11 | 6 | 16 | Make UI responsive on mobile; UI/UX review and improvements; Implement event reminder emails; Deploy landing page content; Cross-browser and mobile testing; User feedback implementation
Sprint 12 | 7 | 19 | End-to-end testing; Security audit and penetration testing; Bug fixes and security patching; Optimize database and performance; Documentation and user guides; Deploy backend to production; Final front-end deployment test
Sprint 13 | 5 | 11 | Final bug-fix on vercel; Code refactoring and cleanup; Final documentation updates; Project presentation ; Final deployment and release tagging
Sprint 2 | 7 | 20 | Develop user registration UI; Implement OTP generation and email service; Create OTP verification API endpoint; Build frontend OTP entry screen; Integrate frontend with auth APIs; Implement session management with JWT; Testing: Verify signup flow end-to-end
Sprint 3 | 6 | 18 | Define user roles in system; Implement role-based authorization on backend; Implement role-based routing on frontend; Build basic dashboard UI skeleton; Create landing page; Testing: Ensure access control
Sprint 4 | 6 | 15 | Design 'Create New Event' form UI; Implement live preview of event details; Set up Event data model in database; Develop backend API to create event request; Connect frontend form to backend; Testing: Create sample event requests
Sprint 5 | 7 | 17 | Build 'Approve Events' admin page UI; Implement backend API to fetch pending events; Implement backend API to approve an event; Implement option to reject event requests; Integrate approval/rejection actions on frontend; Send notification email upon approval/rejection; Testing: Verify admin approval process
Sprint 6 | 6 | 23 | Create database of venues/classrooms; Backend API to check room availability; Backend API to book a classroom; Build 'Book Classroom' UI page; Integrate booking flow with events; Testing: Ensure double-booking prevention
Sprint 7 | 9 | 28 | Extend 'Create Event' form to include service requests; Update event data model to store requested services; Create 'Service Request' sub-model; Generate service request entries upon approval; Build Department Dashboard UI; Backend API to fetch service requests; Backend API to update request status; Integrate department UI with backend; Testing: Validate service request flow
Sprint 8 | 8 | 20 | Develop 'Manage Events' page UI; Backend API to retrieve events by owner; Event edit functionality on frontend; Backend API to update event details; Implement event cancellation option; Backend API to cancel an event; Integrate edit and cancel actions; Testing: Verify event edits and cancellations
Sprint 9 | 7 | 17 | Build 'Upcoming Events' page UI; Backend API to list upcoming events; Implement RSVP functionality on backend; Implement ability to cancel RSVP; Frontend RSVP actions integration; Update event model to track RSVPs; Testing: RSVP flow validation